## BOM
THEWEBXITE — BILL OF MATERIALS
Phan's Custom Tailor website (phase 1)
Date | 23 October 2026
Client | Phan's Custom Tailor (anh Phan Thịnh, chị Phan Thương)
Project | Turn the mock-up into the official three-language website, with the AI fitting room integrated
Prepared By | Xin, TheWebxite
RATE | Man-day rate |  | 3000000
No. | Description | MD | Unit Price | Amount
PHASE 1 — OFFICIAL WEBSITE
1 | Design and build of the three-language mock-up (already done) | 0
✓ 72 pages in English, Vietnamese and Chinese; new design and motion
✓ Kept from the current site: Koalendar booking on the page, the 7 articles, cloth information, contact
✓ New: price list, the tailoring process, a shop with filters, WhatsApp/Zalo buttons, an enquiry form
2 | Phan's real content | 1
• Replace the sample photos with real photos of the villa, the founders, garments and cloth
• Add the missing prices, founding year, turnaround time and holiday closures
3 | Showcase shop | 0.5
• Real products: Nobility cloth and ready-made pieces, with filters
• Customers browse, then ask on WhatsApp/Zalo or book; no cart or online payment yet
4 | Final translations | 0.5
• Review English, Vietnamese and Chinese; apply Phan's corrections
5 | Google and moving from the current site | 0.5
• Old Google links forward to the new pages, so ranking is kept
• Sitemap, Google Business (Maps) link, visitor tracking
6 | AI fitting room integration (Anywear) | 0.5
• Attach the fitting room to product photos, pick the pieces that render well, test on phones
• Privacy notice before a visitor turns on the camera
▶ Anywear usage fees (if the paid plan is chosen) are paid by Phan's directly to Decart and are not in this quote. See the appendix.
7 | Domain, hosting and launch | 0.5
• Set up hosting, point phanscustomtailor.com, https certificate
• Email info@phantailor.com unchanged; the old site runs until switch-over
8 | Testing and handover | 0.5
• Test on computers and phones, fix issues, walk-through for Phan's
Subtotal — OFFICIAL WEBSITE
TOTAL MAN-DAYS / SUBTOTAL
50% DEPOSIT ON CONFIRMATION
50% BALANCE ON COMPLETION
TOTAL PROJECT VALUE
Timeline: about one working week from when we receive all photos and details.
Excludes: domain renewal (Phan's already pays this), AI fitting room usage fees, payment gateway fees.
Yearly hosting and maintenance: quoted separately.
Quotation valid for 30 days.
PHASE 2 — OPTIONAL
PHASE 2 — OPTIONAL
9 | Online sales and payment | 4
• Cart, checkout, order confirmation emails
• VNPay or OnePay gateway (Phan's registers; transaction fees go to the gateway)
10 | Web 3D showcase page | 0.5
• Give the Web 3D team's experience its own page on the site
Subtotal — PHASE 2 — OPTIONAL
Not included in the total project value above. Quoted separately and may be commissioned at any time.
TOTAL IF PHASE 2 COMMISSIONED